BLM Mod.4.4#1: Invention Convention Planning Timeline

Brainstorm for tasks to be undertaken at various points prior to the Invention Convention and add to the list as needed. Establish a realistic work schedule and deadlines.

One Month before Event

- Make a guest list. Consider parents, colleagues from your school and from other schools, superintendents, trustees, local politicians, school benefactors (present and prospective).

- Set a date for the event, as well as an alternate date (check that it does not conflict with other school or community events).

- Reserve facility (e.g., classroom, science room, gymnasium, multipurpose room, library).

Two Weeks before Event

  - Contact media.

  - Make and distribute posters.

  - Prepare and send invitations.

One Week before Event

  - Set up touring schedules for other classrooms.

Three Days before Event

  - Verify attendance of invited guests.

  - Prepare welcoming speeches accordingly.

Night before Event

  - Set up facility.

Day of Invention Convention